## Slide 1: May The Force (Account) Be With You
Presented By:
Zara Hoch
OHM Advisors – Knoxville

## Slide 2: What is a Force Account?
Method by which a Municipality/Utility District completes work using their own personnel, equipment, and resources
An alternative to traditional bid contracts
Applicable to projects that qualify for funding/reimbursement

## Slide 3: Procurement Methods Comparison
Work performed by Municipality/Utility using own personnel and resources
Costs of labor, equipment, and materials are directly documented and paid for by the Municipality/Utility
Traditional Bid-Contract
Work performed by consultant/contractor selected through competitive bidding process
Costs are determined by contract, usually using lump sum or unit prices
Force Account
“Yoda’s Species.” Wookieepedia, Fandom, Inc., 2020, https://starwars.fandom.com/wiki/Yoda%27s_species. Accessed 11 Aug. 2026.
“Hover Pram.” Wookieepedia, Fandom, Inc., 2019, https://starwars.fandom.com/wiki/Hover_pram. Accessed 11 Aug. 2026.

## Slide 4: Benefits of a Force Account
Project scope flexibility
Potential construction cost savings
Davis-Bacon Labor Compliance not typically required unless above a specific threshold
  May reduce administrative burden associated with bidding and managing a federally-funded contract
  Example: ARP requires Davis-Bacon on projects over $10M
Important to Note: Local and State minimum wage requirements will need to be followed

## Slide 5: Benefits of a Force Account
Depending on funding source, internal labor can count as in-kind match
  Documented labor/equipment costs can go towards local match requirements
  In-kind match is not always included in the total funding reimbursement
“Stormtrooper Corps (Legends).” Wookieepedia, Fandom, https://starwars.fandom.com/wiki/Stormtrooper_Corps/Legends. Accessed 11 Aug. 2026.
.

## Slide 6: Disadvantages of a Force Account
Greater administrative effort – the Utility/Municipality acts as the Prime Contractor
  Responsibilities include:
    Documentation
      Material cost estimates
      Equipment logs and usage
      Tracking internal and supplemental labor time
      Receipts
    Schedule
      Meeting funding source benchmarks and deadlines
      Coordinating and managing Subcontractors
    Audits
    Frequent communication/coordination between funding facilitator, utility/municipality, engineer, etc.
    Submissions to regulatory and funding agencies
    Organizing state required inspections based on funding source

## Slide 7: Disadvantages of a Force Account
Utility/Municipality manages procurement and vendors
  Purchasing or renting equipment
  Purchasing materials
  Potential for multiple material bid contracts
Scheduled routine maintenance and emergency response scenarios limit crew resources
Important to Note: Each of these steps will need to meet municipality/utility procurement policies and can add additional time to project schedule

## Slide 8: Best Applications
Best Suited For
  Larger Utilities/Municipalities with dedicated maintenance/construction crews
  Organizations with strong internal project management and documentation

## Slide 9: Best Applications
Ideal Project Types
  Equipment replacements (pumps, membranes, grinders, etc.)
  Smaller, less complex projects
  Construction that can be completed with existing equipment and staff
Aficionadofan. “Classic Image: Falcon Fine-Tuning!” Star Wars Aficionado, 24 Aug. 2013, https://starwarsaficionado.blogspot.com/2013/08/classic-image-falcon-fine-tuning.html.

## Slide 10: Best Applications
When It Makes Sense
  Projects below procurement/bid thresholds
  When consultant involvement and engineering oversight can be minimized

## Slide 11: Summary
Don’t jump before you look!
Evaluate your project before you select the procurement method
Understand the administrative effort required
Document, document, communicate, document!
Administrative/Engineering costs can often outweigh construction savings on large complex projects

## Slide 12
Chris Strupp, P.E.
Project Manager
Nashville, TN
chris.strupp@ohm-advisors.com
Zara ‘ZZ’ Hoch, P.E.
Project Manager
Knoxville, TN
zara.hoch@ohm-advisors.com